## Project Planner
SBML Converter for ERODE
Select a period (week) to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 18 |  |  | Plan Duration |  |  |  | Actual Start |  |  | % Complete |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | WEEKS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Define Project Plan | 1 | 4 | 1 | 4 | 100%
Familiarize with SBML & JSBML | 2 | 6 | 2 | 6 | 100%
Create and runs JSBML demos | 3 | 2 | 3 | 4 | 100%
Setup Project Infrastructure | 3 | 1 | 3 | 1 | 100%
Write first drafts for the introductory sections of the Report | 4 | 2 | 4 | 7 | 100%
Implement a simple SBML converter supporting ERODEs operators | 6 | 2 | 6 | 6 | 100%
Test converter during implementation | 6 | 2 | 6 | 6 | 100%
Extend the converter to support the full SBML operator interface | 9 | 2 | 11 | 2 | 100%
Test converter extension during implementation | 10 | 2 | 11 | 2 | 100%
Improve converter structure and design by refactoring | 13 | 3 | 13 | 3 | 100%
Maintain tests and test new features | 13 | 3 | 13 | 3 | 100%
Document the converter design and implementation | 13 | 4 | 13 | 4 | 100%
Document testing | 14 | 3 | 14 | 3 | 100%
Complete the last converter changes | 15 | 2 | 15 | 2 | 100%
Complete the report | 16 | 3 | 16 | 3 | 100%